## Project Plan and Gantt
Project Name | QuanLyBanDienThoaiDiDong
Project Manager | N.P.Q.Thắng
Project Deliverable
Scope Statement:
Start Date | 2016-09-15
End Date | 2015-10-14
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | N.P.Q.Thắng | 2016-09-15 | 2016-09-16 | 1 | Complete
Agree on objectives | N.P.Q.Thắng | 2016-09-16 | 2016-09-16 | 0 | Complete
Detailed Reqs. | N.P.Q.Thắng | 2016-09-17 | 2016-09-18 | 1 | Complete
Techincal Reqs. | Ng.Minh Vĩ | 2016-09-17 | 2016-09-18 | 1 | Complete
DB Development | Ng.Minh Vĩ | 2016-09-18 | 2016-09-20 | 2 | Complete
Connect DB | Ng.Văn Cương | 2016-09-20 | 2016-09-21 | 1 | Complete
Insert DB | Ng.Minh Vĩ | 2016-09-21 | 2016-09-24 | 3 | Complete
Class Dien Thoai | Ng.P.Q.Thắng | 2016-09-21 | 2016-09-24 | 3 | Complete
Class Nha San Xuat | Ng.Văn Cương | 2016-09-21 | 2016-09-24 | 3 | Complete
From Giao Dien | N.P.Q.Thắng | 2016-09-24 | 2016-09-26 | 2 | Complete
Them Dien Thoai | Ng.P.Q.Thắng | 2016-09-29 | 2016-10-04 | 5 | In-program
Sua Dien Thoai | Ng.Văn Cương | 2016-09-29 | 2016-10-04 | 5 | In-program
Xoa Dien Thoai | Ng.Minh Vĩ | 2016-09-29 | 2016-10-04 | 5 | In-program
Connect WS | team | 2016-10-04 | 2016-10-05 | 1 | Not started
System Testing | team | 2016-10-05 | 2016-10-10 | 5 | Not started
Launch |  | 2016-10-10 | 2016-10-10 | 0

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address
Nguyễn Phan Quốc Thắng | Team leader | 1. Make the plan of the project. 2. Assign task for your member. 3. Analysis & design the system. 4. Code. 5. Write document | thang.nguyen2196@gmail.com
Nguyễn Minh Vĩ | Developer | 1. Design GUI/database. 2. Code. 3. Test | nmvminhvi96@gmail.com
Nguyễn Văn Cương | Developer | 1. Design GUI/database. 2. Code. 3. Test | cuongnguyence140895@gmail.com

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team